CONCEPT NOTE TO SCALE DIGITAL INCLUSION THROUGH MOBILE LABORATORY INTEGRATION

Target Location: Rural communities across Mpigi and Butambala Districts, Uganda

Project Duration: 12 months

Target Groups: School-going children (9-17 years), out-of-school youth (18-30 years), and women entrepreneurs

Total Direct Beneficiaries: 2,180 individuals (1,440 children, 120 youth, 500 entrepreneurs, 120 teachers)

Indirect Beneficiaries: 20,000+ individuals (through trained teachers, peer learning, digital learning portal, and business networks)

# 1. Background and Problem Statement

Uganda faces a critical digital divide that perpetuates inequality and limits economic opportunities for rural communities. While the digital economy is expanding rapidly, rural youth, children, and women entrepreneurs remain systematically excluded from these opportunities due to multiple interconnected barriers:

- Limited Access to Technology: According to the 2024 Population Census report, between 48%-70% of youth in rural areas are Not in Employment, Education or Training (NEET). Most have never touched a computer.

- Educational Exclusion: Rural schools lack computer laboratories, electricity, and internet connectivity. Only 16% of rural schools have functional ICT infrastructure.

- Skills Gap: Youth complete education without employable digital skills, making them uncompetitive for modern jobs or remote work opportunities.

- Business Growth Barriers: Small businesses struggle to adopt digital tools for operations and financial management, limiting their ability to scale, access credit, or become bankable.

- Geographic Isolation: Children, youth, and women from remote rural areas cannot access existing training facilities, creating a second-tier exclusion within already underserved communities.

Over the last 6 months, Code and Smile Foundation has been addressing these challenges through three distinct but complementary programs operating from our Community Innovation Hub in Mpigi. We have successfully reached over 254 youth and children, providing them with basic digital skills and specialization training to drive both employment and entrepreneurship.

The Critical Gap: Increasing Reach

However, our current capacity to reach the most remote rural areas in the districts we serve severely limits our ability to transform more livelihoods. Children, youth, and women from areas distant from our Community Innovation Hub in Mpigi struggle to access our facility. Additionally, we cannot scale our services to reach more schools and communities because we lack a reliable means of transport to deploy mobile training services.

To create systemic change and meaningful impact at scale, we must dramatically increase the geographic area we can serve. This requires a mobile laboratory—a dedicated, equipped vehicle that brings digital skills training directly to remote communities and schools.

# 2. The Mobile Laboratory Solution

A mobile laboratory is the key intervention that will unlock our ability to scale all three programs simultaneously and reach underserved communities that have been left behind.

## 2.1 What Is a Mobile Laboratory?

Our proposed mobile laboratory is a mini-van equipped with:

- 10 laptops with pre-installed educational software, coding tools, and offline learning resources

- Portable internet connectivity (mobile hotspot with sufficient data capacity)

- Power backup system (portable solar panels and battery bank to ensure uninterrupted training in areas without electricity)

- Projector and screen for group instruction and demonstrations

- Robotics kits and STEM learning materials (micro:bit controllers, sensors, building materials)

- Secure storage compartments to protect equipment during transport

This mobile setup eliminates the three biggest barriers to digital skills training in rural Uganda: lack of equipment, unreliable electricity, and transportation challenges.

## 2.2 How the Mobile Laboratory Transforms Our Programs

Program 1: Ignite Program Scale-Up

Current State (Without Mobile Lab):

- Operates only during school holidays (3 times per year)

- Limited to children who can travel to our Mpigi hub

- Reaches only 105 learners annually

- No teacher training or institutional impact

Transformed State (With Mobile Lab):

- Year-round implementation directly in schools

- Partnerships with 48 rural primary and secondary schools

- 1,440 students trained directly in digital literacy, robotics, and STEM

- 120 teachers trained through Training of Trainers (ToT) model

- 19,200 students reached indirectly through trained teachers and digital learning portal

- Expanded curriculum including robotics, micro:bit programming, and STEM experiments

Program 2: Untapped Village Project Expansion

Current State (Without Mobile Lab):

- Limited to youth who can travel to Mpigi hub

- 120 youth trained annually

- Many remote rural youth cannot participate due to transportation costs and time constraints

Transformed State (With Mobile Lab):

- Weekend community bootcamps in extreme rural areas

- Expanded capacity to 120 additional youth annually through mobile outreach

- Total annual reach: 240 youth (120 at hub + 120 through mobile lab)

- Access to youth from the most marginalized communities who previously had zero opportunities

Program 3: Digital Financial Literacy Expansion

Current State (Without Mobile Lab):

- Quarterly workshops at Mpigi hub

- 200 entrepreneurs served annually

- Limited to women and youth who can afford transport to Mpigi

Transformed State (With Mobile Lab):

- Monthly workshops directly in remote rural communities

- 600 entrepreneurs trained annually

- Practical digital tools training where businesses actually operate

- Direct partnerships with village savings groups and women's cooperatives

# 3. The Digital Learning Portal: Multiplying Impact

Beyond the mobile laboratory, our digital learning portal is a critical tool for extending our reach far beyond direct training sessions.

## 3.1 What Is the Digital Learning Portal?

The Code and Smile Foundation Digital Learning Portal is an online and offline platform that provides:

- Comprehensive digital literacy courses covering computer basics, Microsoft Office, internet safety, and AI fundamentals

- Interactive STEM learning modules with illustrated scientific experiments and mathematical explanations

- Robotics and coding tutorials for micro:bit programming and basic web development

- Business and entrepreneurship resources including templates for financial tracking, business planning, and digital marketing

- Offline access capability so learners can continue studying without internet connectivity

## 3.2 How the Portal Extends Our Reach

- Continuous Learning: Students and teachers can access materials after mobile lab visits, reinforcing skills and exploring advanced topics

- Teacher Support: The 120 trained teachers can use portal resources to continue teaching digital literacy throughout the year, effectively multiplying our impact to 19,200+ students

- Peer Learning: Student digital ambassadors trained during mobile lab sessions share portal access with classmates

- Self-Paced Advancement: Motivated learners can progress beyond basic training to advanced specializations

- Resource Efficiency: The portal reduces need for printed materials and allows one training session to have lasting impact

The combination of mobile laboratory visits and the digital learning portal creates a sustainable ecosystem where direct training catalyzes ongoing, self-directed learning across entire school communities.

# 4. Integrated Impact: Expected Outcomes

## 4.1 Direct Beneficiaries (12 Months)

- Ignite Program: 1,440 school children trained in digital literacy, robotics, and STEM

- Teacher Training: 120 teachers trained as digital literacy instructors

- Untapped Village Project: 120 additional out-of-school youth trained through mobile bootcamps (240 total including hub-based training)

- Digital Financial Literacy: 500 entrepreneurs trained in digital business tools

Total Direct Beneficiaries: 2,180 individuals

## 4.2 Indirect Beneficiaries

- Students taught by trained teachers: 19,200 students (120 teachers × 160 students each over the year)

- Digital learning portal users: Estimated 1,000+ learners accessing resources independently

- Family members and employees: Entrepreneurs share skills with household members and staff

Total Indirect Beneficiaries: 20,000+ individuals

## 4.3 Institutional Impact

- Schools Reached: 48 rural primary and secondary schools

- Communities Served: 12-15 remote rural communities in Mpigi and Butambala

- Sustainable Capacity: 120 teachers empowered to continue digital literacy instruction beyond project period

- Youth-Led Enterprises: Estimated 30-40 new businesses launched by trained youth

## 4.4 Long-Term Transformation

- Reduced Youth Unemployment: Measurable decrease in NEET rates in target communities

- Increased Digital Literacy: Rural communities transition from digitally excluded to digitally engaged

- Economic Growth: Local businesses become more efficient, profitable, and bankable

- Educational Improvement: Enhanced STEM learning improves academic performance and university readiness

- Gender Equity: Increased participation of women and girls in technology and entrepreneurship

# 5. Implementation Plan

## Phase 1: Acquisition and Setup (Months 1)

- Procure and equip mobile laboratory van

- Purchase 10 laptops, projector, power backup system, and internet connectivity equipment

- Install secure storage and configure equipment for mobile use

- Recruit and train 4 additional facilitators and 1 driver

- Enhance digital learning portal with additional content and offline capabilities

- Conduct school and community mapping in Mpigi and Butambala districts

## Phase 2: Pilot and Launch (Month 2)

- Pilot mobile lab operations in 6 schools

- Refine logistics, training schedules, and teacher training approach

- Establish partnerships with district education offices

- Launch first community bootcamps for youth

- Begin entrepreneur workshops in remote areas

## Phase 3: Full Implementation (Months 3-10)

- Deploy mobile lab to 48 schools (6 schools per month)

- Train 120 teachers through ToT model

- Reach 1,440 students directly with digital literacy and STEM training

- Conduct weekend bootcamps reaching 120 out-of-school youth

- Deliver monthly entrepreneur workshops in 12 communities (500 total participants)

- Monitor and evaluate program effectiveness

## Phase 4: Consolidation and Sustainability (Months 11-12)

- Conduct follow-up visits to schools to support teacher-led instruction

- Document best practices and lessons learned

- Establish school-based ICT clubs supported by digital ambassadors

- Support enterprise launches for trained youth

- Conduct comprehensive impact evaluation

- Develop partnerships for Year 2 expansion

# 6. Budget Summary

| Budget Category | Amount (USD) |
| --- | --- |
| Mobile Laboratory Vehicle (Mini-van) | 20,000 |
| Equipment & Technology |  |
| • 10 Laptops | 5,000 |
| • Projector and Screen | 800 |
| • Power Backup System (Lithium Battery) | 1,500 |
| • Internet Connectivity (Mobile Hotspot + Annual Data) | 600 |
| • Robotics Kits and STEM Materials | 2,500 |
| Program Implementation |  |
| • Ignite Program (School Training) | 6,000 |
| • Untapped Village Bootcamps | 4,000 |
| • Digital Financial Literacy Workshops | 3,000 |
| • Digital Learning Portal Enhancement | 1,500 |
| Staff Costs |  |
| • 4 Facilitators (12 months) | 12,000 |
| • 1 Driver (12 months) | 2,400 |
| • Program Coordinator (12 months) | 3,600 |
| Operations |  |
| • Fuel and Transportation | 8,000 |
| • Vehicle Insurance and Maintenance | 4,000 |
| • Learning Materials and Supplies | 1,500 |
| Monitoring, Evaluation & Reporting | 6,000 |
| TOTAL PROJECT BUDGET | USD 82,400 |

Note: Detailed line-item budget available upon request. Budget accounts for maintenance, fuel, insurance, and operational costs throughout the project period.

# 7. Monitoring and Evaluation

## Key Performance Indicators

Quantitative Indicators:

- Number of schools reached

- Number of students trained (by age, gender, school level)

- Number of teachers trained and actively using digital literacy skills

- Number of youth completing Untapped Village bootcamps

- Number of entrepreneurs trained

- Digital learning portal usage metrics (users, sessions, completion rates)

Qualitative Indicators:

- Pre- and post-training digital skills assessments

- Student confidence levels in using technology

- Teacher feedback on training quality and sustainability

- Youth employment and business creation rates (6-month follow-up)

- Entrepreneur revenue growth and digital tool adoption

## Data Collection Methods

- Attendance registers and participant demographics

- Skills assessments before and after training

- Quarterly teacher progress reports

- Youth and entrepreneur follow-up surveys

- Focus group discussions with beneficiaries

- Digital learning portal analytics

- Case studies of successful learners and businesses

# 8. Sustainability Strategy

This project is designed for long-term sustainability:

- Teacher Capacity Building: 120 trained teachers become permanent digital literacy resources in their schools, continuing instruction long after mobile lab visits

- Digital Learning Portal: Continuous access to learning materials ensures skills development continues independently

- Student Digital Ambassadors: Peer-to-peer learning extends reach within schools

- School ICT Clubs: Student-led clubs maintain engagement and provide hands-on practice

- Institutional Partnerships: Memoranda of Understanding with district education offices ensure ongoing support

- Asset Creation: Mobile laboratory remains as organizational asset for continued use beyond project period

- Revenue Generation: Trained entrepreneurs generate income, creating economic sustainability in communities

# 9. Risk Management

| Risk | Mitigation Strategy |
| --- | --- |
| Vehicle Breakdown or Accidents | Comprehensive insurance coverage, regular maintenance schedule, trained driver, GPS tracking system |
| Poor Road Conditions in Remote Areas | Four-wheel drive mini-van selection, proper route planning, alternative scheduling during rainy season |
| Equipment Damage or Theft | Secure storage compartments, equipment insurance, overnight security at community innovation hub, proper handling training |
| Low School Participation | Early engagement with head teachers and district education officers, flexible scheduling aligned with school calendars, parent sensitization |
| Electricity/Power Challenges | Portable solar power system and battery backup ensure independence from grid power |
| Teacher Turnover After Training | Train multiple teachers per school (4 per school), provide ongoing support through digital portal, establish teacher networks |
| Limited Youth Participation in Bootcamps | Weekend scheduling to accommodate farming activities, community mobilization through local leaders, incentives like certificates and job placement support |
| Low Entrepreneur Attendance | Partner with existing savings groups and cooperatives, schedule workshops on market days, demonstrate immediate practical value |

# 10. Why This Investment Matters

- Proven Track Record: Code and Smile Foundation has successfully trained 254 beneficiaries in 6 months; this project scales our tested model

- Cost-Effective Scaling: One mobile laboratory unlocks access to 2,180 direct beneficiaries and 20,000+ indirect beneficiaries

- Multiplier Effect: Teacher training and digital learning portal create lasting impact that extends far beyond initial training

- Addresses Root Causes: Eliminates transportation barriers that prevent rural communities from accessing digital skills training

- Integrated Approach: Serves children, youth, and entrepreneurs simultaneously, creating comprehensive community transformation

- Measurable Results: Robust M&E framework ensures accountability and demonstrates tangible impact

- Aligned with National Priorities: Supports Uganda's Vision 2040 digital transformation goals

# 11. Conclusion and Call to Action

The digital divide in rural Uganda is not an inevitable reality—it is a solvable problem. Code and Smile Foundation has the expertise, community trust, and proven programs to transform lives at scale. What we lack is the mobility to reach those who need us most.

A single mobile laboratory is the key that unlocks digital inclusion for thousands of rural Ugandans who have been left behind. With this investment, we will:

- Bring digital skills training directly to 48 rural schools

- Transform 2,180 lives through direct training

- Reach 20,000+ individuals through teacher training and our digital learning portal

- Create sustainable pathways to employment and entrepreneurship

- Build a foundation for long-term economic growth in marginalized communities

We invite partners, donors, and stakeholders to join us in making digital inclusion a reality for rural Uganda. Together, we can ensure that no child, youth, or entrepreneur is left behind in the digital age.

For more information or to discuss partnership opportunities:

Code and Smile Foundation

Tel: +256 752 627 003 or +256 790 359 312

Email: info@casacademy.org

Website: www.casacademy.org